## TMF FD
TMF Fundamental Documents Tracker
Gray Highlighted Cells with an asterisks (*) - Protocols have planned archival and will not have additional updates to Fundamental Documents (TMF Index, TMF Plan, ESM) per DAIDS decision.
Yellow - TMF Plan
Blue - TMF Index
Green - ESM
Protocol | TMF Initiation Date | First Participant Enrolled Date | Retrospective Filing Completion Date | Study Status (as of 11/30/2024) | Study Status Date (as of 11/30/2024) | Start (1 Year from FPI) | Conduct - Closed to Accrual | Close - POS/PAC | TMF Plan Version History | TMF Index Version History | ESM Version History | Planned TMF Archival (Yes / TBD)
IMPAACT 2017 | 2021-08-30 | 2019-04-03 | 2021-10-22 | Closed to Accrual | 2023-08-03 | 2020-04-03 | 2023-08-03 | N/A | Version 1.0 08/24/2021 Version 2.0 09/11/2023 | Version 1.0 01/03/2018 Version 2.0 02/08/2021 Version 3.0 08/09/2021 Version 4.0 09/11/2023 | Version 1.0 08/06/2021 Version 2.0 09/12/2023 | TBD
IMPAACT 2040 | 2024-02-20 | Pending | Pending | Pending | 2024-02-16 | N/A | N/A | N/A | Version 1.0 01/26/2024 | Version 1.0 02/01/2024 | Version 1.0 01/17/2024 | TBD
HPTN 084 | 2020-08-17 | 11/27/2017 | 2021-09-17 | Closed to Accrual | 2020-11-08 | 2018-11-27 | 2020-11-08 | N/A | Version 1.0 08/07/2020 Version 2.0 09/07/2021 Version 3.0 07/13/2022 Version 4.0 12/29/2022 | Version 1.0 01/03/2018 Version 2.0 04/20/2020 Version 3.0 08/09/2021 Version 4.0 07/11/2022 Version 5.0 12/29/2022 | Version 1.0 08/03/2021 Version 2.0 07/08/2022 Version 3.0 01/04/2023 Version 4.0 03/15/2023 | TBD
A5300B | 2022-01-21 | 06/13/2019 | 2022-08-31 | Enrolling | 2019-06-13 | 2020-06-13 | 2025-07-31 | N/A | Version 1.0 01/14/2022 Version 2.0 04/10/2023 Version 3.0 11/14/2024 | Version 1.0 01/21/2022 Version 2.0 04/07/2023 | Version 1.0 01/19/2022 Version 2.0 06/01/2023 | TBD
A5359 | 2022-02-23 | 05/06/2019 | 2022-09-30 | Closed to Accrual | 2024-04-16 | 2020-05-06 | 2024-04-16 | N/A | Version 1.0 02/18/2022 Version 2.0 04/10/2023 Version 3.0 11/14/2024 | Version 1.0 02/22/2022 Version 2.0 05/16/2022 Version 3.0 04/07/2023 | Version 1.0 02/15/2022 Version 2.0 05/12/2022 Version 3.0 06/01/2023 | TBD
A5418 | 2022-09-16 | 09/08/2022 | 2022-10-19 | Closed to Accrual | 2024-11-27 | 2023-09-08 | 2024-11-27 | N/A | Version 1.0 09/07/2022 Version 2.0 04/10/2023 Version 3.0 11/14/2024 | Version 1.0 09/07/2022 Version 2.0 04/07/2023 | Version 1.0 09/02/2022 Version 2.0 06/01/2023 | TBD
IMPAACT 2023 | 2022-04-18 | 10/05/2022 | 2022-05-18 | Enrolling | 2022-10-05 | 2023-10-05 | N/A | N/A | Version 1.0 04/14/2022 Version 2.0 06/06/2023 | Version 1.0 04/18/2022 Version 2.0 05/16/2022 Version 3.0 06/06/2023 | Version 1.0 04/07/2022 Version 2.0 05/12/2022 Version 3.0 05/24/2023 | TBD
IMPAACT 2034 | 2022-06-27 | 2023-10-03 | 2022-07-27 | Enrolling | 2023-10-03 | 2024-10-03 | N/A | N/A | Version 1.0 06/17/2022 Version 2.0 06/27/2023 | Version 1.0 06/16/2022 Version 2.0 06/27/2023 | Version 1.0 06/23/2022 Version 2.0 06/27/2023 | TBD
HPTN 083 | 2020-08-17 | 12/19/2016 | 2021-09-17 | Closed to Accrual | 2020-03-16 | 2017-12-19 | 2020-03-16 | N/A | Version 1.0 08/07/2020 Version 2.0 09/07/2021 Version 3.0 07/13/2022 Version 4.0 02/16/2023 | Version 1.0 02/08/2018 Version 2.0 06/11/2020 Version 3.0 08/12/2021 Version 4.0 07/11/2022 | Version 1.0 08/03/2021 Version 2.0 07/08/2022 | TBD
IMPAACT 2036 | 2023-01-30 | 2024-01-24 | 2023-02-28 | Enrolling | 2024-01-24 | 2025-01-24 | N/A | N/A | Version 1.0 01/25/2023 | Version 1.0 01/25/2023 | Version 1.0 01/25/2023 | TBD
HPTN 083-01 | 2021-12-20 | 07/06/2020 | 2022-05-31 | POSPAC | 2024-07-05 | 2021-07-06 | 2022-01-10 | 2024-07-05 | Version 1.0 12/17/2021 Version 2.0 02/28/2023 | Version 1.0 12/17/2021 Version 2.0 03/03/2023 | Version 1.0 12/10/2021 Version 2.0 03/08/2023 | TBD
HPTN 084-01 | 2021-12-20 | 12/03/2020 | 2022-05-31 | Closed to Follow Up | 2023-01-10 | 2021-12-03 | 2021-08-06 | N/A | Version 1.0 12/17/2021 Version 2.0 02/28/2023 | Version 1.0 12/17/2021 Version 2.0 03/03/2023 | Version 1.0 12/10/2021 Version 2.0 03/08/2023 | TBD
*IMPAACT 2007 | 2020-08-17 | N/A | N/A | Concluded | 2022-11-02 | N/A | N/A | N/A | Version 1.0 08/14/2020 | Version1.0 10/01/2018 Version 2.0 04/20/2020 | N/A | Yes - Complete
*IMPAACT 2014 | 2021-08-30 | 07/02/2018 | 2021-10-22 | Concluded | 2023-12-18 | 2019-07-02 | 2020-02-26 | 2022-05-25 | Version 1.0 08/24/2021 Version 2.0 11/11/2022 | Version 1.0 01/03/2018 Version 2.0 06/23/2020 Version 3.0 08/09/2021 | Version 1.0 08/06/2021 | Yes - Complete
*MTN-034 | 2021-10-22 | 02/06/2019 | 2022-03-20 | POSPAC | 2023-01-13 | 2020-02-06 | 2020-06-30 | 2023-01-13 | Version 1.0 10/20/2021 Version 2.0 10/24/2022 | Version 1.0 10/22/2021 | Version 1.0 10/05/2021 | Yes - YR2025
*MTN-042 | 2021-10-22 | 02/07/2020 | 2022-03-20 | Closed to Follow Up | 2024-05-13 | 2021-02-07 | 2023-05-15 | N/A | Version 1.0 10/20/2021 Version 2.0 11/11/2022 | Version 1.0 10/22/2021 | Version 1.0 10/05/2021 | Yes - YR2025
*MTN-043 | 2021-10-22 | 09/24/2020 | 2022-03-20 | POSPAC | 2024-05-28 | 2021-09-24 | 2021-07-30 | 2024-05-28 | Version 1.0 10/20/2021 Version 2.0 11/11/2022 | Version 1.0 10/22/2021 | Version 1.0 10/05/2021 | Yes - YR2025
*IMPAACT 2019 | 2021-12-16 | 09/09/2020 | 2022-05-31 | POSPAC | 2022-06-14 | 2021-09-09 | 2021-06-28 | 2022-06-14 | Version 1.0 12/10/2021 Version 2.0 01/25/2023 | Version 1.0 12/16/2021 Version 2.0 02/24/2023 | Version 1.0 11/09/2021 Version 2.0 02/23/2023 | Yes - Complete
*IMPAACT 2032 | 2021-12-16 | 03/31/2021 | 2022-05-31 | POSPAC | 2022-11-28 | 2022-03-31 | 2022-01-21 | 2022-11-28 | Version 1.0 12/10/2021 Version 2.0 03/06/2023 | Version 1.0 12/16/2021 Version 2.0 03/09/2023 | Version 1.0 11/09/2021 Version 2.0 03/24/2023 | Yes - Complete

## Legend
Keywords | Description
TBD | To be determined. A date has not yet been determined and will be discussed.
N/A | Not applicable. The data does not exist due to study closure or data not otherwise being relevant.
TMF | Trial Master File (TMF)
ESM | Electronic Systems Mapping document
Color Key
Gray Highlighted Cells with an asterisks (*) | Protocols have planned archival and will not have additional updates to Fundamental Documents (TMF Index, TMF Plan, ESM) per DAIDS decision.
Yellow | TMF Plan
Blue | TMF Index
Green | ESM

## FD Tracker Version History 2023 (hidden)
Version History
Version Number | Version Date | History of Changes
0.01 | 2023-01-09 | Administrative changes related to set-up of template
0.02 | 2023-01-20 | Updates to target dates, per communications with DAIDS
0.03 | 2023-01-22 | Updates to target dates, per communications with DAIDS
0.04 | 2023-01-31 | Updated Study Status and Status Date as of 2023-01-31 Updates to Annual Review dates for IMPAACT 2023, IMPAACT 2034, IMPAACT2032, A5359, A5418, and A5300B per communications with DAIDS
0.05 | 2023-03-28 | Updated Study Status and Status Date as of 2023-02-28 Update to HPTN083 TMF Plan v4.0 Updates to ACTGx3 Timelines Revised timelines for all studies to reflect study status change
1 | 2023-04-05 | Version 1.0 posted to NIH Box
2 | 2023-05-05 | Version 2.0 Posted to NIH Box Updates to A5300B, A5418, A5359 TMF Plan & Index current versions
3 | 2023-06-05 | Version 3.0 Posted to NIH Box Updates to A5300B, A5418, A5359 ESM Update to IMPAACT 2023 ESM
4 | 2023-07-05 | Version 4.0 Posted to NIH Box Updates to IMPAACT 2023 and IMPAACT 2036
5 | 2023-08-15 | Version 5.0 Posted to NIH Box Updates to IMPAACT 2017 timelines Updates to IMPAACT 2040
6 | 2023-09-12 | Version 6.0 Posted to NIH Box IMPAACT 2040 Status changed to "In Development"
7 | 2023-10-10 | Version 7.0 Posted to NIH Box Updates to IMPAACT 2040 Timelines Updates to IMPAACT 2017 TMF Plan, Index and ESM version history
8 | 2023-11-14 | Version 8.0 Posted to NIH Box IMPAACT 2034 Study Status Change to Enrolling
9 | 2023-12-12 | Version 9.0 Posted to NIH Box

## FD Tracker Version History
Version History
Version Number | Version Date | History of Changes
1 | 2024-01-12 | version 1.0 posted to NIH Box IMPAACT 2014 Study Status changed to Concluded IMPAACT 2017 Study Status changed to Closed to Accrual IMPAACT 2036 Study Status changed to Open to Accrual IMPPACT 2019 & 2032 Planned Archival 2024
2 | 2024-02-12 | version 2.0 posted to NIH Box IMPAACT 2040 TMF Plan, Index and ESM Finalized
3 | 2024-03-04 | version 3.0 posted to DAIDS RSC TMF Website Columns Start, Conduct and Close added to tracker.
4 | 2024-04-03 | version 4.0 posted to DAIDS RSC TMF Website IMPAACT 2036 Study Status changed to Enrolling
5 | 2024-05-02 | version 5.0 posted to DAIDS RSC TMF Website A5359 Study Status changed to Closed to Accrual
6 | 2024-06-05 | version 6.0 posted to DAIDS RSC TMF Website
7 | 2024-07-08 | version 7.0 posted to DAIDS RSC TMF Website MTN-042 Study Status change to Closed to Follow Up MTN-043 Study Status change to POSPAC
8 | 2024-08-06 | version 8.0 posted to DAIDS RSC TMF Website HPTN083-01 Study Status changed to POSPAC
9 | 2024-09-05 | version 9.0 posted to DAIDS RSC TMF Website IMPAACT 2014 TMF archive complete
10 | 2024-10-02 | version 10.0 posted to DAIDS RSC TMF Website A5418 Closed to Accrual date changed
11 | 2024-11-01 | version 11.0 posted to DAIDS RSC TMF Website IMPAACT2019 and IMPAACT2032 TMF archive complete
12 | 2024-12-02 | version 12.0 posted to DAIDS RSC TMF Website A5418 Study Status changed to Closed to Accrual Version 3.0 TMF Plans added for A5300B, A5359, and A5418
13 | 2025-01-06 | version 13.0 posted to DAIDS RSC TMF Website

## RSC Proposed Milestones (hidden)
Step | Owner | Task | Version Start | Business Days | Version End
1 | RSC | RSC drafts protocol-specific Index & Plan from DAIDS approved network template (or other reference as directed by DAIDS) | 0 | 10 | 0.1
2 | RSC | RSC posts documents to SharePoint for DAIDS PC and AS review | 0.1 | 1 | 0.1
3 | PCs, AS | DAIDS PCs and AS comment on documents | 0.1 | 10 | 0.2
4 | RSC | RSC provides documents containing comments from DAIDS PCs and AS to the DAIDS TMF Team for review within 1 business day of close of comment period. | 0.2 | 1 | 0.2
5 | DAIDS TMF | DAIDS TMF Team reviews comments from DAIDS PCs and AS and returns the documents to RSC for finalization. | 0.2 | 10 | 0.3
6 | RSC | RSC incorporates DAIDS TMF Team's final comments into documents | 0.3 | 6 | 0.4
7 | RSC | RSC completes editorial review of the documents | 0.4 | 3 | 0.5
8 | RSC | RSC sends near final documents to DAIDS TMF Team for approval signature | 0.5 | 1 | 0.5
9 | DAIDS TMF | DAIDS TMF Team approves, signs, and distributes protocol specific documents | 0.5 | 3 | 1

## ACTGx3 timelines (hidden)
Good afternoon RSC,
Below is the timeline for the annual review of the TMF Indexes for A5359, A5418, and PHOENIx.
Revised Timelines
Protocol | Current Index Version, Date | Update Index Version | Deadline
A5359 | V2.0, 5/16/2022 | V3.0 | 2023-04-10
A5418 | V1.0, 9/7/2022 | V2.0 | 2023-04-10
A5300B / I2003B / PHOENIx | V1.0, 1/21/2022 | V2.0 | 2023-04-10
Revised timelines as of 03/27/2023
Additionally, the RSC wanted to clarify if the document finalization dates for both the TMF Plan and Index should be revised given the following adjustments to timelines for previous milestones within the annual review process:
TRP review deadline was extended from February 17, 2023 to February 28, 2023.
The DAIDS TMF Team Index comments review period is extended through today, March 22, 2023 (original deadline was March 14, 2023).
The RSC proposes the following adjustments to the timelines for the remaining milestones:
RSC processes updates and finalizes the TMF Indices for signature – April 7, 2023 (current deadline March 31, 2023)
Index is signed and distributed by DAIDS TMF Team – April 10, 2023 (current deadline April 3, 2023)
Previous timelines
RSC processes updates and finalizes Indexes for signature – 3/31/2023
Index is signed and distributed by DAIDS TMF Team – 4/3/2023
We would also like the review and updates for the TMF Plans to be completed by the deadlines above so that the Indexes, Plans, and ESMs can all be distributed together.
Please let the TMF Team know if you have any concerns with this timeline by 1/27/2023.
Previous timelines
Protocol | Current Index Version, Date | Update Index Version | Deadline
A5359 | V2.0, 5/16/2022 | V3.0 | 2023-04-03
A5418 | V1.0, 9/7/2022 | V2.0 | 2023-04-03
A5300B / I2003B / PHOENIx | V1.0, 1/21/2022 | V2.0 | 2023-04-03

## IMPAACT 2023 timelines (hidden)
Good morning RSC,
Below is the timeline for the annual review of the TMF Index for IMPAACT 2023.
Protocol | Current Index Version, Date | Update Index Version | Deadline
IMPAACT 2023 | V2.0, 5/16/2022 | V3.0 | 2023-06-08
Proposed Annual Review Timeline:
RSC to post draft protocol Index for AS and PC Review – 4/21/2023
AS and PC Review comments due – 5/5/2023
RSC provides all review comments to DAIDS TMF Team – 5/8/2023
DAIDS TMF Team responds to all review comments – 5/22/2023
RSC processes updates and finalizes Indexes for signature – 6/6/2023
Index is signed and distributed by DAIDS TMF Team – 6/8/2023
We would also like the review and updates for the TMF Plan to be completed by the deadlines above so that the Index, Plan, and ESM can all be distributed together.
Please let the TMF Team know if you have any concerns with this timeline by 2/3/2023.

## IMPAACT 2034 timelines (hidden)
Good morning RSC,
Below is the timeline for the annual review of the TMF Index for IMPAACT 2023.
Protocol | Current Index Version, Date | Update Index Version | Deadline
IMPAACT 2034 | V1.0, 6/16/2022 | V2.0 | 2023-06-22
Proposed Annual Review Timeline:
RSC to post draft protocol Index for AS and PC Review – 5/5/2023
AS and PC Review comments due – 5/19/2023
RSC provides all review comments to DAIDS TMF Team – 5/22/2023
DAIDS TMF Team responds to all review comments – 6/6/2023
RSC processes updates and finalizes Indexes for signature – 6/20/2023
Index is signed and distributed by DAIDS TMF Team – 6/22/2023
We would also like the review and updates for the TMF Plan to be completed by the deadlines above so that the Index, Plan, and ESM can all be distributed together.
Please let the TMF Team know if you have any concerns with this timeline by 2/3/2023.
Email dated 5/23/2023 from RSC TMF
Good evening Melissa,
We acknowledge receipt of your email and RSC has noted that the DAIDS TMF Team will need until June 9, 2023 to provide feedback on the IMPAACT 2034 TMF Index document. Given this shift, please confirm that the remaining steps in the review process for the IMPAACT 2034 TMF Index should be adjusted as shown in the table below. Additionally, please confirm that the review and update tasks for the TMF Plan should follow the same timeline so that the Index, Plan, and ESM can all be distributed together, per the DAIDS TMF Team’s prior decision.
IMPAACT 2034 TMF Index Review Timeline:
Task | Target date 1/27/2023 | Target date 5/23/2023
RSC to post draft protocol Index for AS and PC Review | 2023-05-05 | Completed 5/5/2023
AS and PC Review comments due | 2023-05-19 | Completed 5/19/2023
RSC provides all review comments to DAIDS TMF Team | 2023-05-22 | Completed 5/22/2023
DAIDS TMF Team responds to all review comments | 2023-06-06 | 2023-06-09
RSC processes updates and finalizes Index for signature | 2023-06-20 | 2023-06-23
Index is signed and distributed by DAIDS TMF Team | 2023-06-22 | 2023-06-27
Please confirm by May 25, 2023 that target timelines for the IMPAACT 2034 TMF Index and TMF Plan reviews will be adjusted as shown in the table above.
Email dated 5/24/2023 DAIDS RSC TMF
Good morning, There are no concerns with this adjustment. Melissa